## Sheet1
6.27.19
Gilford Butler School Estimated Cost Comparison New Construction vs. Renovation
| Build New 4500 SF (1) | Renovate 4500 SF (2) | Build New Temp Move (3) | Renovate Temp Move (4) | Comments
Base Cost | 1012500 | 1145300 | 1012500 | 1145300 | Based on John Hanson's Report 5/21/19
Demolition Cost | 75000 | 0 | 75000 | 0 | Approximate estimate obtained by John Spear
Temporary Move Cost | 0 |  | 75000 | 75000 | Actual estimate range is $26,000 to $36,000
Less Temp. Move Cost Improvements |  |  |  | -75000 | Assumes ramps, fire alarms, ADA bathrooms not be completed twice
Sub Total | 1087500 | 1145300 | 1162500 | 1145300
Architectural/Engineering/Other Fees | 119625 | 183248 | 127875 | 183248 | 11% new construction, 16% renovation per John Hansen
Contingency | 54375 | 114530 | 58125 | 114530 | 5% new construction, 10% renovation per John Hansen
Total Capital Project | 1261500 | 1443078 | 1348500 | 1443078
Maintenance Cost -Total 4 years | 4000 | 25000 | 169999.61 | 169999.61 | Guesstimate based on adjusted historical usages - $42,500 per year
Total w/ 4 Years Maintenance | 1265500 | 1468078 | 1518499.61 | 1613077.61
Increase from Build New, No Temp Move |  | 202578 | 252999.61 | 347577.61
Notes:
1. Build new assumes school building is demolished as soon as feasible after town acquires clear title. Four year estimate to build is based on average build new times for other area projects studied.
2. Renovation is for a portion of the first floor of the school-4500 of the 6500 SF. Lower level of building would be closed to the public. Does not include structural upgrades that may be required.
3. Temp move is to renovate a portion necessary to obtain temporary permit from Fire Marshal's Office. Lower level of the building would be closed to the public. Temporary move costs do not include roof, heating system or other major repairs.
4. Assumes the $ 26-75K temp move costs are able to credited to the overall renovation costs.
5. Demolition cost is assumed to be the responsibility of the Town of South Thomaston
6. All estimates are approximate and based on 2019 dollars and assumed no volunteer or reduced rate labor, materials and equipment.